- Project Information

Project Title: Business-Aligned Job Hunt

Project Manager: Daniel Aldana

Project Description: Conduct an accurate and honest job hunt to prepare for internships, part-time, or entry-level opportunities in business and technology. The main deliverables expected are a job application package (e.g., resumes, documents), network portfolio/tracker, and mock interview documentation.

Project Closure Type: Changed Priority Closure – Stopped due to strategy shift

Closing Summary: Overall, I’m proud of my performance and execution throughout this semester-long project. Some of the goals were met, including expanding my LinkedIn profile by at least two connections and practicing and holding three interviews, encouraging the interviewer to ask me questions when I explained my project to them. Expanding my network and strengthening my communication skills was a great success; however, maintaining confidence and motivation proved to be a challenge, mainly when life’s issues arose during the execution phase. Although I did not fully complete what I needed to deliver, I believe the project was overall a success, with a satisfaction and success rating of 7 out of 10.

- Deliverables Summary

| Deliverable Name | Original Definition of Done | Actual Progress | Status |
| --- | --- | --- | --- |
| Job Application Package (Resume Set + Cover Template) | Final files exported in professional format (PDF). Content aligned with at least two to three real job postings. Reviewed by a professor or career counselor. Includes documented version history (v1 → v2). | Constructed a resume that matches similar job requirements across multiple positions Documented version history and area of revisions | Yellow |
| Networking Portfolio (Contacts + Informational Interviews) | Log includes contact names, organizations, discussion topics, and follow-up actions. Reflections recorded for each interview. Evidence of connections and interactions captured via screenshots or LinkedIn activity. | Connected with 4 new people on LinkedIn Communicated with my new LinkedIn connections in person/online with two of them to maintain relationship Documented three reflections for each interview I executed. | Green |
| Application Tracker (Pipeline + Follow-Ups) | Each record includes company name, role, submission date, and next action. At least one follow-up completed for each open application. Weekly updates maintained through project completion. | Minimal to no progress conducted | Red |
| Interview Readiness Kit (Q&A Bank + Mock Feedback) | Final Q&A document submitted. At least two mock interview feedback forms or screenshots included. Documented revisions showing applied feedback. | Received two interview feedback and interviewees explained strengths and area of improvements Documented feedback to showcase growth for future interview opportunities | Green |

- Change Log

| Change No | Change Date | Change | Reason for Change |
| --- | --- | --- | --- |
| 1 | Week 9 Date: 2025-10-19 | Changed Project Scope from CIS focus to Business Focus. To accurately describe the scope of my project, I decided to rename my project title and changed appropriate sections to fit my new scope, while keeping the IS/IT/Cybersecurity emphasis. | The reason I made this change was because when conducting my usual job searching, I noticed that some of the technology focus position falls under business operations, such as business analyst, sales operations, and some I found with marketing / social media marketing. This allowed me to expand my opportunities when choosing potential job positions. |

- Performance Analysis

Budget Performance:

Despite being a student and most services and tools being provided for free, either fully (ChatGPT) or with limited access (Monday.com), unexpected costs arose for a tool during the project's closure phase. I found myself during week 12 needing to pay $25 for an AI model to create my closure website. The AI model, called Lovable, was worth the cost because it excels at making applications and websites. Since I’ve taken Web Design and Development, I’ve been able to implement my knowledge in UX/UI design, all for the cost of $25. Other than this, no unexpected costs for tools, hosting, or any resources appeared.

Schedule Performance:

To a moderate extent, I did meet my milestones throughout my project timeline. Initially, I started rough but managed to pick up the pace quickly. However, in the middle of my execution, I found myself delaying key deliverable milestones that were approaching, needing to change deadlines to give me ample time to complete them. While smart to do, I ended up doing more work than planned to the point where some of the key milestones were done with poor quality, such as job requirement analysis and scheduling stakeholder feedback, or didn’t initiate, such as cover letter creation due to focusing on resumes and other milestones (e.g., interviewing). The reasoning for the delays was a lack of confidence and motivation, as well as concentrating on different courses and limited job opportunities, despite broadening my scope. Although there were delays, I believe that my time estimates were realistic throughout this project, except for my own lack of motivation, which prevented some key milestones from being completed within the expected timeframe of 2-4 days with excellent quality. Giving myself 1-2 weeks for key milestones was more than enough for me to complete; however, delays got the better of me, and thus, some of the semester’s milestones were met rather than fully completed.

- Stakeholder Management

My communication skills at the start of the semester were weak, and to some extent, they remain a weakness of mine; however, they have improved thanks to this semester-long personal project. Initially, engaging with stakeholders was challenging due to nerves and judgment, which is why my initial communication with stakeholders was limited to professors, peers, and friends I had known from prior semesters. However, over time, I met new people, both through force (e.g., group projects) and on my own time (reaching out on LinkedIn). Now, I’m more comfortable reaching out to new stakeholders on my own, with minimal or no nerves and fear of judgment. The reason being that I managed to approach each stakeholder with a direct, personal tone, stating, “I’m doing a personal project, may you please review it and provide feedback. Feel free to ask me for any clarification you may need.”

Throughout my communication with stakeholders, feedback was essential to me for review and implementation, as it not only strengthened my confidence but also allowed me to gain insight into others’ points of view on job searching, having been in their position before. They know the struggles and fears that come with applying, yet these stakeholders managed to overcome obstacles and landed a position in the workforce. While all feedback was valuable, the single most useful was “make applying mechanical, not emotional”, meaning: Don’t let your emotions delay your chances of applying to jobs, make it a habit to apply automatically and deal with the emotions later. Rejection is inevitable, and learning from it is the best outcome for the future.

- Risk and Issue Summary

The main issue throughout my project execution was delays in key milestones, which were initially a planned risk before the execution phase; however, it didn’t take long before that risk turned into an issue that I needed to address quickly. While delays caused havoc and disrupted smooth progress from start to closure, the reasoning behind them changed, and I’ll explain each, along with providing the weeks it affected.

Within my first few weeks of executing this project, specifically 6 and 7, a sudden health issue arose, and I needed to prioritize my health over academic work, not just for this class, but for others as well. Thus, with the amount of work piling up, many of my early deliverable tasks were delayed or conducted with poor quality. However, during week 8, I had improved at managing deadlines while focusing on my health. By the end of the week, I had caught up with all my tasks. However, little did I know that another delayed wave was about to occur.

During the middle of my execution, in weeks 9, 10, and 11, I realized that there were hardly any job opportunities to which I could apply, with one position being reasonable for me every couple of days. With this, I expanded my scope from a CIS focus to a business focus, hoping to find more positions that involved some technical skills or CIS concepts, but were more business-oriented. While this helped for a short period, it wasn’t enough, and I needed to adjust some of the deadlines and, to a certain extent, shift the project's priority focus in week 12 to focus solely on creating resumes for the available positions, communicating with stakeholders, and practicing interviews.

Moving forward, I will focus on and monitor potential risks for future projects, as deadlines were significantly altered throughout my execution due to these risks becoming issues. Despite being mainly a solo project, communication is key when you need feedback or for sudden incidents that occur and disrupt your project progress. This will enable me to keep my teammates informed about potential issues and alleviate stress not only for myself but also for others.

- What Went Well?

Following up with my team to keep everyone on track went well, as I communicated with each member regarding any issues or deadlines, whether related to the course or personal matters. Furthermore, I ensured that each of my teammates was up to date on their project progress and showcased this progress in the team charter, as I was sometimes responsible for submitting their work on their behalf.

Furthermore, changing the project methodology from predictive to hybrid allowed my workflow to be more reasonable and smooth, especially regarding resume construction. Since issues arose early on during the execution phase, a hybrid approach enables me to change deadlines and modify the structure of planned deliverables for future execution.

Lastly, stakeholder feedback enabled me not only to improve my project execution but also to boost my personal confidence level, as many of the stakeholders I reached out to showed support for my accomplishments, even if they were small. Additionally, some of my stakeholder feedback motivated me to expand my social circles, as many expressed that I have strong communication skills, and that my doubts and fear of judgment are holding me back.

- What Didn’t Go Well?

The main issue I faced was balancing coursework with project execution. As explained earlier, maintaining deadlines was a struggle. During the execution phase, numerous deadlines were adjusted, despite employing a hybrid approach and preparing in advance for potential deadline issues. The issues persisted, and attempts to minimize them were unsuccessful, as they continued to occur during the project's closure phase.

Furthermore, before the execution phase, my project topic and goal were too vague, as they initially were “Preparing for the CC certification.” While a great project to conduct, the feedback I received from stakeholders (the professor) was that it was a deliverable rather than a goal. Thus, I needed to change my planning and preparation phase to align with my new topic, which was job hunting.

Additionally, documentation of deliverables and their execution was poor, meaning that it wasn’t my priority to complete all deliverables and their tasks to fulfill the full deliverables. For example, for the job packet deliverable, applying to 3–5 positions was merely optional for me, and simply constructing resumes was enough for that deliverable to be completed (in my eyes). An unreasonable shift in priority, caused by missed deadlines, lack of motivation, and other issues, was the reason for the poor quality of deliverables being executed.

- What Would You Do Differently?

For the initiation and planning phase, I would communicate with the stakeholder(s) who provided me with the information about the project (in this case, the professor) to clarify the scope, business needs and values, and other crucial execution details. I would communicate with teammates about the project's objective (in this case, classmates) and understand what needs to be done during future phases of the project.

For the execution and monitoring phase, I would monitor risks and issues more frequently and set reasonable deadlines for deliverables and their associated tasks. Furthermore, I need to update my teammates and stakeholders about my problems so that they have a clear understanding of why the execution and monitoring didn’t go as planned.

Specifically for this project, I would have expanded and focused on other job listing sites such as Indeed, Glassdoor, and LinkedIn for job positions and internships, rather than solely focusing on Handshake. I may have missed out on opportunities that were in my favor based on my experiences and academic achievements. This may be added to my roadmap section as a suggestion for future job hunt processes.

- Lessons Learned Register

| Date | SDLC Stage | What was the problem? | What was the consequences? | Lesson Learned Advice |
| --- | --- | --- | --- | --- |
| Week 5 September 16, 2025 | Planning | Project topic was a deliverable rather than a goal Preparing for the CC certification could have been a deliverable for my now project topic of job hunting | My project charter filled in sections needed to be changed completely Planning phase was rough as preparation for execution was a rough transition | Communicate to stakeholder about business needs (professor needs) Allow room for mistakes as I loss motivation entering execution phase |
| Week 6 September 27, 2025 | Execution | Health related issues arose Needed to focus on myself rather than my courses | Deadlines were changed heavily Future execution processes were done in poor quality due to early rough start Workload piled up, resulting in speedy completion (poor quality) | Allow time for myself Communicate with stakeholders regarding poor quality work or delayed processes |
| Week 9 October 18, 2025 | Execution | Lack of job / internships opportunities Needed to broaden project scope | Delayed deadlines regarding stakeholder communications / feedbacks on deliverables Loss in potential opportunities in job / internships | Strengthen my initiation and planning phase Analysis issues and improve project topic and goal Expect and prepare for scope changes |
| Week 11 November 1, 2025 | Monitoring | Lack of documentation despite execution was on track at the time Documentation needed for deliverable completion | Unprepared when stakeholders viewed and ask about my project progress Lack of evidence of deliverable completion | Know when project phases shifts, if not, communicate with project managers (professor) Documented when execution phase initiate |
| Week 13 November 15, 2025 | Closing | Stakeholder interviews and feedback deadlines was approaching and changing it isn’t an option Stakeholder feedback documentation was needed for my project completion | Preventable stress occurred Communication with stakeholder for interviews was difficult due to busy schedule Unnecessary rushing to find available stakeholders | Remind myself and teammates about upcoming deadlines Prioritize deliverables and tasks early on Keep calm under pressure |

- Key Takeaways for Future Projects

- Analyze and communicate about project needs and requirements early on

  - Communicate with stakeholders about the project’s goals, needs, values, scope, and other relevant information necessary during the initialization and planning phases.

  - For me, I needed to completely change my project goal due to the vagueness in my initial project idea, which resulted in a rough transition to execution.

- Monitor my risk register more often.

  - Many risks I had considered turned out to be issues during the execution phase, resulting in slow progress, poor quality execution, and delays in meeting deadlines.

  - Communicating with teammates and stakeholders should have been my priority in explaining why the progress and process of deliverables and tasks have been smooth.

  - Communicate with the team and stakeholders to obtain guidance on addressing issues and monitoring risks.

- Schedule stakeholder feedback early on

  - Although I did inform some stakeholders that I might need their feedback and critiques regarding my project in the future, I never followed up when I had the chance midway through the execution phase, resulting in preventable stress and busy scheduling for feedback sessions/interviews.

  - Ensure that documentation of scheduling and feedback is conducted during the execution phase, rather than the monitoring phase, due to a shift in priority when it comes to the monitoring and closing phases of the project. (Less time to fine stakeholder feedback due to busy schedule).

- Formal Sign-Off

Project Manager Print Name: Daniel Aldana

Project Manager Signature:

Tech Owls: I spoke with my team about the outcomes of my project, my deliverables, and the processes of these deliverables through smaller tasks on December 6, 2025. My team expressed support for the results of my project. It acknowledged the difficulty of the job hunting process, especially in terms of the lack of internship positions available that fit our needs and values. They valued my personal goals of finding an internship to achieve my mission and vision statement. They encouraged me to continue searching for and applying to positions, letting this project serve as a stepping stone for future job hunts. They signed off on December 6, 2025.

Interviewees (Keiley Anaya, Roshan Roy Suja, and Juan Manuel Toledo): I spoke with Keiley, Roshan, and Juan about the progress of my project, the results, and the outcomes of my deliverables in terms of completion. On December 5, 2025, each of my interviewees agreed that I could’ve made more progress on my deliverables, especially regarding personal issues such as my fear of rejection and the emotions that rushed through me when considering applying for an internship. However, they mentioned that the project idea was great for me to choose, as it aligns with my personal goals and values. This was not just a random choice; furthermore, Keiley added that I was honest throughout my project, especially in discussing the issues I faced and the lack of motivation I experienced when applying to positions. Regarding my interview performance, Juan appreciated the outcome of my network portfolio and interview, as he mentioned that I demonstrated professionalism and knowledge about the questions I provided to each of the interviewees, adding that I may already possess strong communication and interviewing skills. They signed off on December 5, 2025.

- Recognition

My Tech Owl Teammates: Angel, Fatima, Abner, Berenice

I’m grateful that I met and communicated with them not only about our academic course and this project, but also for the opportunity to connect and get to know them on a more casual level. I envision myself speaking to each of these members next semester, and for most of them, even after I graduate, as well as to the others. For this project, I am grateful for the feedback I received throughout the semester, from planning to the project's closure phase. I believe that I provided enough input not only on their project, but also on their academic choices, since, as mentioned before, tech owls are graduating soon (some even this semester). My team provided scope suggestions and recommendations from stakeholders for interviews, and we met once a week to discuss our project progress. If any were confused or stuck on something in this project, we helped each other out, and in the end, we were stress-free, until the next issue arose.

Professors: Arun Aryal, Daniel Razmjou, Maria Espinoza

Each of these professors provided interest and offered guidance regarding my project and the job process in general. Once in a while, Arun would follow up with me on how I was doing with my project and, in general, how the course was going, since he teaches that course as well. I mentioned that (at the time of asking) the workload was heavy, but explained that it set the class up for the execution phase, especially learning and applying scope, triple constraints, values, along with understanding what deliverables are and who the potential stakeholders are. Daniel provided insight regarding project executions and the issues projects face. Furthermore, he provided resources regarding certifications, which enabled me to pass an entry-level certification. Maria, throughout the semester, provided insight not only on project management but also on stakeholder relationships, as everyone is likely to face challenging stakeholders in the workplace. Furthermore, she provided feedback to me regarding confidence when applying to positions, stating that I should make it a habit to, one, ignore emotions when applying (and deal with them later), and, most importantly, two, expect rejection; it’s bound to happen to everyone.

Interviewees: Keiley Anaya, Roshan Roy Suja, Juan Manuel Toledo

These peers, whom I’m fortunate enough to have met this year, all had something in common when viewing my project charter and explaining what my project is: they all celebrated small accomplishments that I had previously overlooked. For starters, I managed to reach out and ask for interviews before asking these three interviewees, which Keiley explained I wouldn’t have done when we first met within the first few months of the year. Furthermore, these interviews allowed me to display professionalism, which was evident in all of them, explaining that they were a bit nervous due to the sudden shift in tone of my communication, as if it were a real job interview. Juan mentioned that this is a great skill to understand when to be professional and when you can be more casual, which aligns with emotional intelligence and understanding social cues. Roshan questioned my project charter not only for his own understanding, but also to test my understanding, as I needed to consider my goals and values when questions about stakeholder relations arose. Overall, Keiley, Roshan, and Juan allowed me to focus on my small achievements and test my understanding of my project, and I’m thankful for choosing them as stakeholders for part of my project.

- What’s Next

Besides focusing on finishing strong in my last semester at CSULA, I will immediately communicate with stakeholders and potential teammates regarding project idea validation, project goals, and the processes that need to be conducted to complete the project thoroughly from the lead stakeholder's perspective (e.g., future professors/managers). I will review my lessons learned registers and analyze the issues regarding the cause, outcomes, and whether the problem was preventable (if so, how would my team or I have addressed it?). These two practices will enable me to start strongly during the initialization and planning phases of the project, as these phases have been challenging from the outset, along with the transitions for this personal project.

I will continue to strengthen my communication skills and expand my social circle. Still, rather than relying on online platforms (e.g., LinkedIn connections), I will focus on socializing in person, so that the relationships are built on face-to-face support and trust. While I understand that this is significantly outside my comfort zone, I will ultimately need to perform this task after graduation and throughout my career. I will improve my communication with stakeholders regarding project feedback and critiques, as it was challenging to schedule stakeholder interviews towards the end of the semester, despite having many opportunities to conduct these interviews early on. There are many other project management concepts that I will strengthen and improve, such as identifying scope, understanding deliverables, and choosing methodologies and tools. However, for me, stakeholder communication and project goals are the priorities that enable me to perform well throughout the project timeline.